## Sheet1
Function | Sub function |  | Activities |  | Estimation (hour)
|  | Front-end | Back-end | DB | FE | BE |  | O | M | L
|  | Requirement |  |  |  |  | 39 |  |  |  | 37.25
Shoping | List products | Implement HTML | Create API | Design DB | 8 | 8 |  | 12 | 16 | 20
|  | Integrate with BE |  |  | 4 | 4 |  | 1 | 8 | 10
| Add to cart | Integrate with BE | Create API | Design DB | 2 | 2 |  | 1 | 4 | 10
| Billing detail | Implement HTML | Create API | Design DB | 12 | 16 |  | 10 | 28 | 40
| Place order | Integrate with BE |  |  | 4 | 4 |  | 4 | 8 | 10
| Payment |  | Research for payment gateway | Design DB |  | 8 |  | 4 | 8 | 16
|  |  | Integrate to payment gateway |  | 16 | 16 |  | 20 | 32 | 36 | three point | PERT
[5 empty] | Total |  | 104 | 52 | 104 | 142 | 99.3333 | 101.6667
|  | Testing |  |  |  |  | 26 |  |  |  | 24.8333
|  | Monitor & Control (Management: meeting, distribute req.,..) |  |  |  |  | 26 |  |  |  | 24.8333
[5 empty] | Total |  | 195
186